Construction Site Progress Capture

Functional and Non-Functional Requirements

| Document owner | Version | Date | Status |
| --- | --- | --- | --- |
| Michael Yaacoub, Sr Solution Engineer | 1.0 | 2026-08-24 | Draft |

This template follows the sample requirements structure: purpose and scope, Epic, Features and User Stories, non-functional requirements, traceability, and assumptions.

# 1. Purpose and Scope

## 1.1 Business Problem and Outcome

Site engineers record daily progress in a notebook and transfer it to a spreadsheet in the site office, so the quantities that drive a monthly valuation are assembled from memory a fortnight after the work happened. Photographic evidence sits on individual phones, weather and labour returns are reconstructed for the delay claim rather than captured as they occurred, and the payment application is challenged because the quantities cannot be evidenced line by line. The outcome this release targets is progress captured against the work package at the point of installation, weather and labour recorded daily as fact, and a valuation produced from that record with the evidence attached.

## 1.2 In Scope

- Daily progress capture against work packages and their measured items, with quantity installed

- Photographic evidence tied to the work package, location and date of capture

- Daily site record: weather observations, labour and plant on site, and disruption events

- Valuation preparation from captured quantities, with quantity surveyor review and approval

- Offline capture anywhere on site, including basements and steelwork, with synchronisation on reconnection

## 1.3 Out of Scope

- Design authoring, drawing revision control and the model federation process

- Procurement, subcontract letting and supplier payment processing

- Programme scheduling and critical path analysis, which remain in the planning system

- Health and safety incident reporting, which is handled by the dedicated safety application

- New analytics beyond the commercial reporting already in service

## 1.4 Success Measures

| Objective | Metric | Target | Measurement source |
| --- | --- | --- | --- |
| Value what was actually built | Valuation lines supported by captured quantities and evidence | Raise from 48 percent to 95 percent | Valuation support audit |
| Shorten the valuation cycle | Elapsed time from period end to submitted payment application | Reduce from 12 days to 4 days | Application submission timestamps |
| Record disruption as it happens | Disruption events recorded on the day they occurred | Raise from 27 percent to 90 percent | Daily site record timestamps |
| Reduce valuation challenge | Valuation lines challenged by the client and subsequently reduced | Reduce from 14 percent to 4 percent | Client certification records |

# 2. Epic

| ID | Epic title | Outcome statement | Business owner |
| --- | --- | --- | --- |
| EPIC-01 | Construction Site Progress Capture | As a construction delivery organisation, we need site engineers to record progress, evidence and daily site conditions against work packages as the work happens, so that valuations are produced from fact rather than recollection and disruption claims rest on a contemporaneous record. | Commercial Director |

# 3. Features and User Stories

## 3.1 FEAT-01 Work Package Progress Capture

Presents the work packages assigned to the engineer with their measured items, and records the quantity installed at the point of work rather than at the end of the month.

| ID | User story | Acceptance criteria | Priority |
| --- | --- | --- | --- |
| US-101 | As a site engineer, I want to record quantity installed against a measured item at the point of work, so that the figure reflects what was built rather than what was remembered. | Given a work package with measured items, when I record a quantity, then it is captured against the item, the location and today's date, and the cumulative quantity against the contract quantity is shown. Given a cumulative quantity would exceed the contract quantity, when I submit, then it is blocked and a variation must be referenced before the excess can be recorded. | Must |
| US-102 | As a project manager, I want progress visible by work package as it is captured, so that I can see the true position without waiting for a monthly return. | Given quantities captured today, when the package view loads, then percentage complete by item and by package reflects captures within 5 minutes. Given a package has had no capture for 7 days, when the view refreshes, then it is flagged as stale so an absence of progress is not mistaken for an absence of recording. | Should |

## 3.2 FEAT-02 Evidence and Location Capture

Ties photographic evidence to the work package, the location on site and the date, so that a photograph can be produced against a valuation line months later without anyone having to remember where it was taken.

| ID | User story | Acceptance criteria | Priority |
| --- | --- | --- | --- |
| US-201 | As a site engineer, I want photographs tied to the work package and location automatically, so that evidence can be found later without searching a camera roll. | Given a photograph captured during a progress entry, when it is stored, then the work package, measured item, grid reference or level and the capture time are recorded with it. Given the device has no connectivity, when I capture evidence, then it is queued locally with its capture time and location preserved and uploads within 5 minutes of reconnection. | Must |
| US-202 | As a quantity surveyor, I want to retrieve the evidence behind any valuation line, so that a client challenge is answered from the record. | Given a valuation line, when I open its evidence, then every photograph and progress entry contributing to that line is listed with its capture date and location. Given evidence is missing for a line, when the valuation is prepared, then the line is flagged as unevidenced rather than included silently. | Must |

## 3.3 FEAT-03 Daily Site Record

Captures the facts of the day as they occur: weather observations, labour and plant on site, and any event that disrupted the works, so a delay claim rests on a contemporaneous record.

| ID | User story | Acceptance criteria | Priority |
| --- | --- | --- | --- |
| US-301 | As a site engineer, I want to record weather, labour and plant daily, so that the site record is contemporaneous rather than reconstructed. | Given a site day, when I complete the daily record, then weather observations at the recorded times, labour by trade and plant on site are captured and the record is locked at the end of the day. Given a day is missed, when it is completed later, then it is marked as a late entry with the actual entry date recorded alongside the site date. | Must |
| US-302 | As a commercial manager, I want disruption events recorded on the day with their effect, so that a claim can be substantiated without reconstructing the sequence. | Given a disruption event, when I record it, then the cause, the work packages affected, the hours lost and any instruction reference are captured with photographic evidence. Given a disruption event is recorded, when the daily record locks, then the event becomes part of the contemporaneous record and cannot be edited. | Must |

## 3.4 FEAT-04 Valuation Preparation and Approval

Assembles the period valuation from captured quantities, flags anything unevidenced, and routes it for quantity surveyor approval before it becomes a payment application.

| ID | User story | Acceptance criteria | Priority |
| --- | --- | --- | --- |
| US-401 | As a quantity surveyor, I want the valuation assembled from captured quantities, so that I review a position rather than compile one. | Given a valuation period, when I prepare the valuation, then every measured item is presented with the quantity captured in the period, the cumulative quantity and the value at contract rates. Given a line has no supporting evidence, when the valuation is assembled, then it is flagged and must be resolved or excluded before approval. | Must |
| US-402 | As a commercial manager, I want valuation approval separated from the person who prepared it, so that no application is submitted on a single pair of eyes. | Given the approver also prepared the valuation, when approval is attempted, then it is blocked by the segregation-of-duties rule and an alternative approver is offered. Given approval is granted, when the record is written, then the valuation and its supporting evidence references are immutable and the application pack can be generated from them. | Must |

# 4. Non-Functional Requirements

| ID | Category | Requirement | Target | Validation |
| --- | --- | --- | --- | --- |
| NFR-001 | Performance | The work package list and progress capture screens render on a site tablet over a mobile network | 95th percentile under 2 seconds; valuation assembly under 30 seconds for 4,000 measured items | Performance test against the production-shaped dataset |
| NFR-002 | Availability | The progress service is available throughout site working hours, including weekend and night shifts | 99.9 percent monthly, measured 06:00 to 22:00 local, seven days | SLO dashboard and monthly service review |
| NFR-003 | Offline / resilience | An engineer can capture progress, evidence and the daily record anywhere on site with no signal | Full offline capture for a 12-hour shift, sync within 5 minutes of reconnection, capture time and location preserved | Chaos and disconnected-device test suite |
| NFR-004 | Security and privacy | Access requires Entra ID single sign-on, and subcontractor users see only their own packages | No cross-subcontractor visibility, verified by an automated authorisation test | Security review and penetration test |
| NFR-005 | Accessibility | Every screen is operable one-handed, with gloves, in bright sun and in poor light, wearing site personal protective equipment | WCAG 2.2 AA, verified outdoors on the target tablet | Automated axe scan plus manual screen-reader audit |
| NFR-006 | Auditability | Every quantity, evidence item, daily record and approval records actor, action, timestamp, location and correlation identifier | 100 percent captured, retained for 12 years to match the contract limitation period | Audit evidence pack sampled each release |
| NFR-007 | Integration | Contract, rate and programme integrations declare timeouts, retries and a defined failure behaviour | No valuation calculated on stale rates; assembly fails closed rather than value at an outdated rate | Contract tests in the integration pipeline |

# 5. Traceability

| Feature | User stories | Screen | Test cases | Primary outcome |
| --- | --- | --- | --- | --- |
| FEAT-01 | US-101, US-102 | SCR-01 | TC-101, TC-102 | Quantities reflect what was built, on the day it was built |
| FEAT-02 | US-201, US-202 | SCR-02 | TC-201, TC-202 | Evidence is findable against any valuation line months later |
| FEAT-03 | US-301, US-302 | SCR-03 | TC-301, TC-302 | Disruption rests on a contemporaneous record rather than a reconstruction |
| FEAT-04 | US-401, US-402 | SCR-04 | TC-401, TC-402 | Valuations are reviewed and approved from fact, and challenged less |

# 6. Assumptions and Out of Scope

## 6.1 Assumptions and Dependencies

- Contract work packages, measured items, contract quantities and rates exist in the commercial system and are exposed through the integration layer.

- Site grid references, levels and zones are defined in the project setup and available to the application.

- Engineers carry corporate-managed tablets with a camera, enrolled in Intune and usable with gloves.

- Subcontractor users are provisioned as external identities scoped to their own work packages.

- Site mobile coverage is intermittent in basements, cores and steelwork rather than absent.

## 6.2 Constraints and Exclusions

- The commercial system remains the system of record for contract quantities and rates; this application may not hold a competing rate schedule.

- The daily site record locks at the end of each site day and cannot be edited afterwards, because it is a contemporaneous record.

- The person preparing a valuation may not approve it, under the commercial control standard.

- Records are retained for 12 years to match the contract limitation period under a deed.

# 7. Approval

| Reviewer | Role | Decision | Comments | Date |
| --- | --- | --- | --- | --- |
| Chris Santaniello | Director, Solution Engineering | Pending | Business sponsor review |  |
| Product owner | Business product owner | Pending | Scope, stories and acceptance criteria |  |
| Delivery lead | Engineering delivery lead | Pending | Feasibility and estimate confirmation |  |